## Work Order
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
WORK ORDER
Cash Book Voucher No. |  |  |  | Date-
Name of Contractor or supplier :
M/s Azab Bahadur $ Son , Bhopaltop, Henry Cross, Noida, ( Formerly M/s Hilltone assoviates), Mumbai
Name of Work ;-
Electric Repair and MTC work at Govt. Ambedkar hostel Ambamata, Govardhanvilas, Udaipur including installation of Air conditioners and all external electrification work, transformer etc ( Job No- 98768/12-0402023)
Serial No. of this bill : |  |  |  | First & Final Bill
No. and date of the last bill- |  |  |  | Not Applicable
Reference to work order or Agreement : |  |  |  | 1179 Dt. 09-01-2025
Agreement No. |  |  |  | 48/2024-25
Date of written order to commence work : |  |  |  | 2025-01-09
St. date of Start : |  |  |  | 2025-01-18
St. date of completion : |  |  |  | 2025-04-17
Date of actual completion of work : |  |  |  | 2025-03-01
Date of measurement : |  |  |  | 2025-03-03
WORK ORDER AMOUNT RS. |  |  |  | 524669
TENDER PREMIUM % |  |  |  | 11.22 | % | ABOVE
Item | Description | Unit | Quantity | Rate | Amount | BSR
1 | supply and fixing of fans |  |  |  |  | 1.5
| 1000 mm | Each | 50 | 1256 | 62800 | 1.5.1
| 1500 mm | Each | 50 | 1472 | 73600 | 1.5.2
| exhaust fans | Each | 50 | 662 | 33100 | 1.5.3
2 | supply and fixing of Lamps |  |  |  |  | 1.7
| On board | Each | 100 | 136 | 13600 | 1.7.1
3 | supply and fixing of Air Conditioner | Each | 10 | 25362 | 253620 | 7.1
4 | supply and fixing of Tube Light | Each | 30 | 50 | 1500 | 7.2
5 | supply and fixing of Stree Light | Each | 10 | 3352 | 33520 | 7.10
471740
52929
524669
Button 1

## Bill Quantity
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
WORK ORDER
Cash Book Voucher No. |  |  |  | Date-
Name of Contractor or supplier :
M/s Seema Electrical Udaipur
Name of Work ;-
Electric Repair and MTC work at Govt. Ambedkar hostel Ambamata, Govardhanvilas, Udaipur
Serial No. of this bill : |  |  |  | First & Final Bill
No. and date of the last bill- |  |  |  | Not Applicable
Reference to work order or Agreement : |  |  |  | 1179 Dt. 09-01-2025
Agreement No. |  |  |  | 48/2024-25
Date of written order to commence work : |  |  |  | 2025-01-09
St. date of Start : |  |  |  | 2025-01-18
St. date of completion : |  |  |  | 2025-04-17
Date of actual completion of work : |  |  |  | 2025-03-01
Date of measurement : |  |  |  | 2025-03-03
WORK ORDER AMOUNT RS. |  |  |  | 524669
TENDER PREMIUM % |  |  |  | 4 | % | ABOVE
Item | Description | Unit | Quantity | Rate | Amount | BSR
1 | supply and fixing of fans |  |  |  |  | 1.5
| 1000 mm | Each | 35 | 1256 | 43960 | 1.5.1
| 1500 mm | Each | 57 | 1472 | 83904 | 1.5.2
| exhaust fans | Each | 50 | 662 | 33100 | 1.5.3
2 | supply and fixing of Lamps |  |  |  |  | 1.7
| On board | Each | 109 | 136 | 14824 | 1.7.1
3 | supply and fixing of Air Conditioner | Each | 9 | 25362 | 228258 | 7.1
4 | supply and fixing of Tube Light | Each | 32 | 50 | 1600 | 7.2
5 | supply and fixing of Stree Light | Each | 14 | 3352 | 46928 | 7.10
452574
18103
470677
Button 1

## Extra Items
EXTRA ITEM SLIP
Name of Work :- |  | Electric Repair and MTC work at Govt. Ambedkar hostel Ambamata, Govardhanvilas, Udaipur
Name of Contractor or supplier : |  |  | M/s Seema Electrical Udaipur
Reference to work order or Agreement : |  |  | 1179 Dt. 09-01-2025
S.No. | Ref. BSR No. | Particulars | Qty. | Rate | Amount | Remarks